## Slide 1: Agile Software Development: Setting the Scene
  Robert Percival
  Partner & Head Technology & Innovation – Canada
  IT.CAN 20th Annual Conference – Montreal – 25 October 2016

## Slide 2: Outline of this part of the discussion
1. | Overview of Agile
2. | Agile project considerations
3. | Contracting for Agile projects
4. | When to use Agile

## Slide 3: Overview of Agile

## Slide 4: What is software development?
A set of steps of phases that a computer program goes through while it is being created
Not just about the code itself
Rather, a structured and planned process from conception to design to creation to deployment
Software development principles have origins in long standing principles utilized in the construction and manufacturing industries
Long standing most well-known and utilized is the “waterfall software development” process

## Slide 5: “Traditional” / waterfall development model

## Slide 6: Main benefits of waterfall development model
Provides a clear and structured way to approach software development projects
Lends itself to identifying clear milestones to track project progress
If the requirements and design are correct at the start of the development project, time and effort and money may be saved

## Slide 7: Issues with waterfall development model
In practice it is difficult to define requirements in clear and unambiguous way at the outset
WDM is not very adaptable to change–assumes requirements can be “frozen” at conclusion of planning phase before moving to design/build stages
  This is often not a likely valid assumption – especially where requirements are not well understood at the project outset
  Required changes not may present themselves until deployment stage where problems / shortcomings in the software can be observed
Changes “up the waterfall” during development often occur – requirements may change during development – due to business changes, changes in law etc. – sends development back to design, re-development etc.
Sequential nature means much up front requirements scoping and design before any development started – much time and money is spent before any tangible deliverables

## Slide 8: Issues with waterfall leads to Agile
S/W dev success statistics are not great*: ~16% success / ~53% completed over budget, over time, or delivered less functionality / ~31% projects cancelled < * See Standish Group’s “Chaos Reports” >
WDM issues lead to development of other methodologies in the 1990’s
Focus was on “iterative” software development
“Agile” is a general term for a several different iterative software development methodologies which all have a core common element:
    the rapid development of software on an iterative basis with working software delivered at the end of each iterative cycle
In 2001 a group of software developers produced the “Manifesto for Agile Software Development” – purpose was to define the values of the so-called Agile movement

## Slide 9: Agile development – the Agile manifesto
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
Individuals and interactions over processes and tools Working software over comprehensive documentation Customer collaboration over contract negotiation Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
© 2001, this declaration may be freely copied in any form, but only in its entirety through this notice

## Slide 10: The 12 principles of the Agile manifesto*
Manifesto supplemented by 12 principles
Resulting focus of ASD has the following primary characteristics:
Iterative development: Bursts of design / build / test / deploy
Functional software: Working software is primary measurement of success
Enabling change: Changing requirements need to be accommodated – even late in the development process
Customer involvement: Developers and business teams (including customer, if external) need close interaction and work together
*See all 12 principles at:
www.agilealliance.org/the-alliance/the-agile-alliance-maifesto/the-twelve -principles-of-agile-software/

## Slide 11: Agile development
Concept
Close

## Slide 12: One common Agile type: Scrum methodology
Product Vision
12
1-4 week Sprint
Sprint Review Meeting
Sprint Planning Meeting
Product Backlog
Sprint Backlog
Product Owner
Finished Product
Daily Sprint Meeting
Legend:
Scrum Master Product Owner Development Team
User Story

## Slide 13: Waterfall vs. Agile
Waterfall
  Strong dependency between phases. Changing requirements are difficult to address
  Progress is measured in deliverable artifacts (e.g. requirement specifications, design documents, test plans)
  Critical design flaws may be discovered too late during development
  Value is delivered at the end of the project and may not meet expectations
  Longer project timeframes
Agile
  Change inherent to the process. Frequent insight on measurable progress aiming at continuous improvement
  Progress is demonstrated through tangible results – working software
  Risks can be identified and remediated early on
  Customers are involved throughout the product development lifecycle
  Requirements are prioritized based on value
  Breaks a complex problem in manageable units of work

## Slide 14: Agile project considerations

## Slide 15: Agile project considerations
Range of Agile projects
    Purely internal vs. external / outsourced Agile project
Contracting models for external / outsourced Agile project
    A range of possible models
Service provider resource location
    Co-located vs. onshore / offshore mix

## Slide 16: Contracting for Agile projects

## Slide 17: Why “traditional” contracts do not work for Agile (and raise issues for lawyers drafting them)
“Traditional” / waterfall contracts are “flawed” when applied to Agile projects because:
  The requirements are fixed at project start
  They mandate sequential development
  Scope, resources and schedule are fixed at the start of the project
  Testing is used as a contractual tool
  While the lawyers remain concerned about:
  Defining the “what” i.e. the work product, specs
  How much it will cost
  How long it will take and when will be delivered
X

## Slide 18: Contracting issues for Agile (Scrum, fully outsourced)
Project/product vision
      Focuses attention on the desired outcome, and acts as a reference point
Product Backlog
      Evolving statement of the customer’s requirements based on the product vision
Key roles and personnel issues
      Product Owner, Development Team, Scrum Master
The Sprint process
      Duration, Sprint planning meeting, daily meetings, Sprint review meetings, starting the next Sprint
Deliverables and acceptance
      “Definition of Done”
      Project completion
    Velocity
        Ensuring the Product Backlog is being cleared as the project progresses
        Tracking progress against projected timeframes

## Slide 19: Contracting issues for Agile (Scrum, fully outsourced)
Pricing
      Range of pricing models – T&M, fixed price project, price per Sprint completed, incentives
Warranties and indemnities
Liability
Termination
      Termination for convenience
IP rights
      IP ownership can be problematic if customer personnel are part of the development team
Dispute resolution
      Possible use of expert determination for technical issues

## Slide 20: When to use Agile

## Slide 21: Requirements for Agile success
Customer engagement, commitment and knowledge of Agile
      Executive level buy-in and organisational acceptance
      Challenges in overcoming waterfall / “traditional” concepts in Agile
      Clarity around priorities and time to market to capture market opportunities
Service Provider experience
      Strong project management
      Empowerment of team members for rapid decision making
      Trust
Recognition of different contracting framework and risk allocations
Early and collaborative engagement with legal counsel who have familiarity with Agile contracting

## Slide 22: When to use Waterfall vs. Agile
Waterfall
Works well in an environment with:
  Fixed scope
  Defined set of requirements
  Defined set of technology
Agile
Works well in an environment with:
  Uncertain level of requirements
  An aligned goal
  High level of agreed user involvement
  Customer targets time-to-market and an ability to react quickly to market changes
  Customer needs to see how development progresses before fully committing

## Slide 23: Wrapping up
Agile development methodologies are a substantial departure from the more traditional waterfall model
Agile projects have the potential to deliver faster and more flexible projects, with potentially shippable software iterations or features
In the same way that Agile methodologies challenge the more traditional concepts of waterfall model software developments, contracting for Agile projects require new ways of thinking and different approaches to common contractual issues

## Slide 24: Contacts
Robert Percival
Partner
Head of Technology & Innovation – Canada
Norton Rose Fulbright
Direct: 416 216 4075
Email: robert.percival@nortonrosefulbright.com

## Slide 27
Disclaimer
  Norton Rose Fulbright US LLP, Norton Rose Fulbright LLP, Norton Rose Fulbright Australia, Norton Rose Fulbright Canada LLP and Norton Rose Fulbright South Africa Inc are separate legal entities and all of them are members of Norton Rose Fulbright Verein, a Swiss verein. Norton Rose Fulbright Verein helps coordinate the activities of the members but does not itself provide legal services to clients.
  References to ‘Norton Rose Fulbright’, ‘the law firm’ and ‘legal practice’ are to one or more of the Norton Rose Fulbright members or to one of their respective affiliates (together ‘Norton Rose Fulbright entity/entities’). No individual who is a member, partner, shareholder, director, employee or consultant of, in or to any Norton Rose Fulbright entity (whether or not such individual is described as a ‘partner’) accepts or assumes responsibility, or has any liability, to any person in respect of this communication. Any reference to a partner or director is to a member, employee or consultant with equivalent standing and qualifications of the relevant Norton Rose Fulbright entity.
  The purpose of this communication is to provide general information of a legal nature. It does not contain a full analysis of the law nor does it constitute an opinion of any Norton Rose Fulbright entity on the points of law discussed. You must take specific legal advice on any particular matter which concerns you. If you require any advice or further information, please speak to your usual contact at Norton Rose Fulbright.